**Contract Fulfilment Time Schedule**

|  |  |  |
| --- | --- | --- |
| **Deadline:** | **Activity:** | **Note:** |
|  | Purchase Contract Conclusion |  |
| within 1 week as of Purchase Contract Effectiveness | Handover of the proforma invoice of 30 % of the total price | Art. VI (1) (a) |
| within 1 month as of Purchase Contract Effectiveness | Handover of documentation and SDK and beginning of the support focusing on the development of the connection of the Device into the Buyer's production system. | Article II (5) and  Article IV (6) |
|  | Device Final Acceptance Tests (FAT) at the manufacturer's facility - before shipping | Article IV (3) |
| within \_\_\_ weeks as of Purchase Contract Effectiveness | Delivery of the Device – signing of the deliver y note | Article IV (1) |
| within 3 weeks after signing the delivery note (delivery of the Device) | Protocol No. 1 signing confirming:   * installation of the Device * commissioning of the Device in offline mode * delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 * training of the Supplier operator and maintenance personnel * Device acceptance tests (SAT) | Article IV (1) and  Article IX (4) |
| Within 10 days after signing of the Protocol No. 1 | Handover of the final invoice of 100 % of the total price | Article VI (1) (b) |
| Depending on the performance of third parties | Start-up and commissioning of the Device in the Buyer's production system | Article IV (5) |
| According to the written information of the Buyer about the connection of the Device to the Buyer's production system | Beginning of the 30-days test run | Article II (2) (b) |
| 30 days after beginning of the test run | End of the 30-day test run  Protocol No. 2 signing, beginning of the warranty period | Article IX (7) |
| 12 months after signing  Protocol No. 2 | End of the warranty period | Article X (2) |

Any changes to this Time Schedule may be made, in justified cases and except for the deadline for Device delivery according to Article IV item 1 of the Contract, in the form of a written protocol signed by authorized representatives of both Contracting Parties.