**Contract Fulfilment Time Schedule**

|  |  |  |
| --- | --- | --- |
| **Deadline:** | **Activity:** | **Note:** |
|  | Purchase Contract Conclusion |  |
| within 1 week as of Purchase Contract Effectiveness | Handover of the proforma invoice of 40 % of the total price | Art. VI (1) (a) |
| Within 22 weeks as of Purchase Contract Effectiveness | Device Factory Acceptance Tests (FAT) at the manufacturer's facility - before shipping | Article IV (2) |
| No later than 10 working days from performing of FAT (obtaining of test samples) | Evaluation and acceptance of FAT results meeting the required parameters by the Buyer - signing of the record on the successful acceptance tests result |  |
|  | In the case of a negative evaluation of the FAT results by the Buyer information to the Seller will be send and a record of the acceptance test result of non-compliance with the required parameters will be signed; Repetition of the FAT should take place no later than 2 weeks after notification of the negative evaluation of acceptance test results. | In case of a negative evaluation of the results of the second FAT test, it is possible to perform the last third FAT, if even after this test the results are not acceptable, the Buyer has the right to withdraw from the Contract. |
| no later than 2 weeks after the notification of successful evaluation of the acceptance tests (FAT) | Delivery of the Device – signing of the delivery note | Article IV (3) |
| within 3 weeks after signing the delivery note (delivery of the Device) | Protocol No. 1 signing confirming:   * installation of the Device * commissioning of the Device * delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 * training of the Buyer operator and maintenance personnel * device acceptance tests in the Buyer’s premises (SAT) * beginning of the 30-days test run | Article II (2) (b), Article IV (4) and  Article IX (4) |
| Within 10 days after signing of the Protocol No. 1 | Handover of the final invoice of 100 % of the total price, payment of 50% of the total price | Article VI (1) (b) |
| 30 days after beginning of the test run | End of the 30-day test run  Protocol No. 2 signing, beginning of the warranty period, final payment of 10% of the total price | Article IX (7), Article VI (1) (c) |
| 12 months after signing  Protocol No. 2 | End of the warranty period | Article X (2) |

Any changes to this Time Schedule may be made, in justified cases and except for the deadline for factory Acceptance tests (FAT) in accordance with Article IV (2) of the Contract, in the form of a written protocol signed by authorized representatives of both Contracting Parties.