|  |  |
| --- | --- |
| **TIME SCHEDULE** | |
|
|  | |
| ***Specification of the phase*** | ***Term of performance/ of delivery*** |
| Design preparation:  2pc of DOVID *(DESIGN 1 + DESIGN 2)* | **Within 20 working days** from the effective date of providing the design templates for DOVIDs parts from the Buyer. |
| Production of Master:  2pc of Master *(DESIGN 1 + DESIGN 2)* | **Within 30 working days** from the Designs approval by the Buyer. |
| Pilots DOVIDs production *(DESIGN 1 + DESIGN 2)* | **Within 30 working days** from the Masters approval by the Buyer. |
| Delivery of foils *(DESIGN 1 + DESIGN 2)* | **Within 50 working days** from the Pilots DOVIDs approval by the Buyer. |