**ATime Schedule**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Deadline**  **for 1st Device:** | **Activity:** | **Note:** |
|  |  | Contract signature |  |
|  |  | Publication of the Contract in the Register of contracts (= taking effect of the Contract) |  |
| #1 | according to Art. VI para. 1 point a) of the Contract | Handover of the proforma invoice of 30 % of the total price | Art. VI para. 1 point a) |
| #2 | Within 24 weeks after taking effect of the Contract | Device Factory Acceptance Tests (FAT) at the Seller’s manufacturing plant - before shipping | Art. IV para. 2 + Art. VIII + Annex No. 7 |
| #3 | next working day after receipt of samples | Evaluation and acceptance of FAT - signing of the report on the successful acceptance tests result.  Details about FAT stated in Article VIII | Art. VIII |
| #4 | no later than 26 weeks after taking effect of the Contract | Delivery of the Device – signing of the Delivery Note | Art. IV para. 3 |
| #5 | 29 weeks after taking effect of the Contract | Protocol No. 1 signing confirming:   * installation of the Device * commissioning of the Device * delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 in Czech language * training of the Buyer operator and maintenance personnel * device acceptance tests in the Buyer’s premises (SAT) * beginning of the 30-days test run | Art. IV para. 4 + Art. IX para. 4 |
| #6 | according to Art. VI para. 1 point b) of the Contract | Handover of the final invoice of 100 % of the total price, payment of 50% of the total price | Art. VI para. 1 point b) |
| #7 | 30 days after beginning of the test run | End of the 30-day test run  signing of the Protocol No. 2 (=beginning of the warranty period) | Art. IX para. 6 |
| #8 | according to Art. VI para. 1 point b) of the Contract | payment in amount of 20% of the total price | Art. VI para. 1 point c) |
| #9 | 12 months after signing  Protocol No. 2 | End of the warranty period | Art. X para. 2 |