**Time Schedule**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Deadline:** | **Activity:** | **Note:** |
|  |  | Contract signature |  |
|  |  | Publication of the Contract in the Register of contracts (= taking effect of the Contract) |  |
| #1 | according to Art. VI para. 1 point a) of the Contract | Handover of the proforma invoice of 30 % of the total price | Art. VI para. 1 point a) |
| #2 | Before delivery of the Device | The Contractor’s proclamation of eligibility of the Device for acceptance by the Client and of the successful testing of the required basic parameters | Art. IV para. 2 |
| #3 | No later than 17 weeks after taking effect of the Contract | * delivery of the software development kit (SDK) and any related technical documentation – confirmed in writing by representatives of Parties authorized to negotiate in factual and technical matters | Art. II para. 2 point a) |
| #4 | No later than 25 weeks after taking effect of the Contract | Delivery of the Device – signing of the Delivery Note | Art. IV para. 3 |
| #5 | No later than 27 weeks after taking effect of the Contract | Protocol No. 1 signing confirming:   * installation and commissioning of the Device * delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 in Czech language * training of the Buyer operator and maintenance personnel * device acceptance tests in the Client’s premises (SAT offline test) * delivery of the SDK | Art. IV para. 4 + Art. VIII para. 3 |
| #6 | No later than 2 weeks after delivery Client's request for SAT in production system | Protocol No. 2 signing confirming:   * device acceptance tests in the Client’s premises (SAT production system test) * beginning of the 30-days test run | Art. IV para. 5 + Art. VIII para. 4 |
| #7 | No later than 31 days after signing Protocol No. 2 | Protocol No. 3 signing confirming:   * end of the 30-days test run * start of the warranty period |  |
| #8 | according to Art. VI para. 1 point b) of the Contract | Handover of the final invoice of 100 % of the total price, payment of 50% of the total price | Art. VI para. 1 point b) |
| #9 | 30 days after beginning of the test run | End of the 30-day test run  signing of the Protocol No. 2 (=beginning of the warranty period) | Art. VIII para. 6 |
| #10 | according to Art. VI para. 1 point c) of the Contract | payment in amount of 10% of the total price | Art. VI para. 1 point c) |
| #11 | according to Art. VI para. 1 point d) of the Contract | payment in amount of 10% of the total price | Art. VI para. 1 point d) |
| #12 | 12 months after signing  Protocol No. 2 | End of the warranty period for the Device | Art. IX para. 2 |