|  |  |
| --- | --- |
| **Innovation of Diffractive Optically Variable Image Device for Electronic ID Cards (eID)**  **TIME SCHEDULE ANNEX 2 to the Framework agreement for supply of security elements for Czech electronic ID cards**  **No. [•]/OS/2020** | |
|
|  | |
| ***Specification of the phase*** | ***Term of performance/ of delivery*** |
| Design preparation | **20 working days** from the signing of the Framework agreement |
| Production of MasterHologram | **20 working days** from the Design approval by the Client |
| Pilot sheets production | **30 working days** from the MasterHologram approval by the Client |
| First Delivery (min. 20 000 pcs of sheets) | **60 working days** from the purchase order (the purchase order will not be sent to Contractor before Pilot sheets approval) |
| Second and other Deliveries | **60 working days** from the purchase order |