**Time Schedule**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Deadline**  **for Device:** | **Activity:** | **Note:** |
|  |  | Contract signature |  |
|  |  | Publication of the Contract in the Register of contracts (= taking effect of the Contract) |  |
| #1 | according to Art. VI para. 1 point a) of the Contract | Handover of the proforma invoice of 30 % of the total price, payment of 30% of the total price | Art. VI para. 1 point a) |
| #2 | Within 48 weeks after taking effect of the Contract | Device Factory Acceptance Tests (FAT) at the Seller’s manufacturing plant - before shipping | Art. IV para. 2 + Art. VIII + Annex No. 8 |
| #3 | next working day after receipt of samples | Evaluation and acceptance of FAT - signing of the report on the successful acceptance tests result.  Details about FAT stated in Article VIII  Protocol of the acceptance tests (FAT) signing, which will document the successful evaluation of the factory acceptance tests (FAT) | Art. VIII |
| #4 | according to Art. VI para. 1 point b) of the Contract | Handover of the proforma invoice of 50 % of the total price, payment of 50% of the total price | Art. VI para. 1 point b) |
| #5 | no later than 50 after taking effect of the Contract | Delivery of the Device – signing of the Delivery Note | Art. IV para. 3 |
| #6 | 52 weeks after taking effect of the Contract | Protocol No. 1 signing confirming:   * installation of the Device * commissioning of the Device * delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 in Czech language * training of the Buyer operator and maintenance personnel * device acceptance tests in the Buyer’s premises (SAT) * beginning of the 30-days test run | Art. IV para. 4 + Art. IX para. 4 |
| #7 | according to Art. VI para. 1 point c) of the Contract | Handover of the final invoice of 100 % of the total price, payment of 10% of the total price | Art. VI para. 1 point c) |
| #8 | 30 days after beginning of the test run | End of the 30-day test run  signing of the Protocol No. 2 (=beginning of the warranty period) | Art. IX para. 6 |
| #9 | according to Art. VI para. 1 point b) of the Contract | payment in amount of 10% of the total price | Art. VI para. 1 point d) |
| #10 | 12 months after signing  Protocol No. 2 | End of the warranty period | Art. X para. 2 |