# Time Schedule – Delivery of the Numbering device

|  | Deadline: | Activity: | Note: |
| --- | --- | --- | --- |
|  |  | Contract signature |  |
|  |  | Publication of the Contract in the Register of contracts (= taking effect of the Contract) |  |
| #1 | within 1 week after taking effect of the Contract, | Handover of the first non-payment bank guarantee which will expire upon the signing of Delivery Note | Art. VI para. 1 point a) and XV para 1 and 2. |
| #2 | according to Art. VI para. 1 point a) and XV para 2 of the Contract. | Handover of the proforma invoice of 30 % of the total price | Art. VI para. 1 point a) |
| #3 | Within 50 weeks after taking effect of the Contract | Factory Acceptance Tests (FAT) at the Contractor’s manufacturing plant - before shipping | Art. IV para. 2 + Art. VIII + Annex No. 8 |
| #4 | next working day after receipt of samples | Evaluation and acceptance of FAT - signing of the Protocol of the acceptance tests (FAT). Details about FAT stated in Article VIII | Art. VIII |
| #5 | according to Art. VI para. 1 point b) | Handover of the proforma invoice of 20 % of the total price after the signing of Protocol of the acceptance tests (FAT) | Art. VI para. 1 point b) |
| #6 | Within 60 calendar days after receiving the Client’s Invitation | Delivery of the Device – signing of the Delivery Note | Art. IV para. 3 |
|  |  | Expire of the first non-payment bank guarantee |  |
| #7 | according to Art. VI para. 1 point c) | Handover of the final invoice of 100 % of the total price, payment of 30 % of the total price after singing of delivery note | Art. VI para. 1 point c) |
| #8 | Within 75 weeks after taking effect of the Contract | Protocol No. 1 signing confirming: - unloading of the Device and transport to the installation site - installation and commissioning of the Device - delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 in Czech language - training of the Client’s operator and maintenance personnel - device acceptance tests in the Client’s premises (SAT) - beginning of the 60-days test run | Art. IV para. 5 and 6+ Art. IX para. 4 |
| #9 | according to Art. VI para. 1 point d) | Payment of 10% of the total price after the singing of Protocol no. 1 (SAT) | Art. VI para. 1 point d) |
| #10 | 60 days after beginning of the test run | End of the 60-day test run, signing of the Protocol No. 2 (=beginning of the warranty period) | Art. IX para. 7 |
| #11 | according to Art. XV para. 4 and 5. | Handover of the second non-payment bank guarantee which will expire upon the end of the warranty period | Art. XV para. 4 and 5 |
| #12 | according to Art. VI para. 1 point e) | Payment in amount of 10% of the total price | Art. VI para. 1 point e) |
| #13 | 12 months after signing Protocol No. 2 | End of the warranty period | Art. X para. 2 |
|  |  | Expire of the second non-payment bank guarantee |  |

# Time Schedule –Expansion of the Device with a Varnishing unit (reserved change to the obligation)

|  | Deadline: | Activity: | Note: |
| --- | --- | --- | --- |
| #0 |  | Application of the reserved changes to the obligation (Request) for Varnishing Unit and the Publication of the Request in the Register of Contracts | Art. XVI para. 2 to 4 |
| #1 | according to Art. VI para. 1 point a) and XV 1. | Handover of the first non-payment bank guarantee which wil expire upon the signing of Delivery | Art. XV para 1 and 2 |
| #2 | according to Art. VI para. 1 point a) of the Contract | Handover of the proforma invoice of 30 % of the total price |  |
| #3 | Within 50 weeks after the Publication of the Request in the Register of Contracts | Factory Acceptance Tests (FAT) at the Contractor’s manufacturing plant - before shipping |  |
| #4 | next working day after receipt of samples | Evaluation and acceptance of FAT - signing of the Protocol of the acceptance tests (FAT). Details about FAT stated in Article VIII |  |
| #5 | according to Art. VI para. 1 point b) | Handover of the proforma invoice of 20 % of the total price for the Supplement of Varnishing Unit to the signing of FAT |  |
| #6 | Within 60 weeks after the Publication of the Request in the Register of Contracts | Delivery of the Device – signing of the Delivery Note |  |
|  |  | Expire of the first non-payment bank guarantee |  |
| #7 | according to Art. VI para. 1 point c) | Handover of the final invoice of 100 % of the total price for the Supplement of Varnishing Unit, payment of 30 % of the total price after singing of delivery note |  |
| #8 | Within 75 weeks after the Publication of the Request in the Register of Contracts | Protocol No. 1 “Varnishing unit” signing confirming: - Unloading of the Varnishing unit and transport to the installation place - Installation of the Varnishing unit into the Device and commissioning of the Device and Varnishing unit - delivery of necessary documents required by the Contract including handover of documents and technical documentation according to Annex No. 2 in Czech language - operator training for whole/expanded Device - Device acceptance tests in the Client’s premises (SAT) - beginning of the 60-days test run |  |
| #9 | according to Art. VI para. 1 point d) | Payment of 10% of the total price after the singing of Protocol no. 1 (SAT) |  |
| #10 | 60 days after beginning of the test run | End of the 60-day test run, signing of the Protocol No. 2 “Varnishing unit” (= beginning of the warranty period) |  |
| #11 | according to Art. XV para. 4. | Handover of the second non-payment bank guarantee which wil expire upon the end of the warranty period |  |
| #12 | according to Art. VI para. 1 point e) | Payment in amount of 10% of the total price for the Supplement of Varnishing Unit |  |
| #13 | 12 months after signing Protocol No. 2 “Varnishing unit” | End of the warranty period |  |
|  |  | Expire of the second non-payment bank guarantee |  |