| Příloha č. 1c ZD Přehled výsledků a výstupů jednotlivých programů EHP a Norských fondů 2009 - 2014 včetně jejich inidkátorů.. CZ02: Biodiversity and Ecosystem Services & Environmental Monitoring and Integrated Planning Control & Adaptation to Climate Change.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 4; 4; 5; Partnership Agreements, Project Monitoring Reports, Web sites of Project Promoters and their Partners. Number of projects with expected shared results (both partners are involved professionally in planning and implementation and can claim credit for achieved results); 0; 0; 0; 14; 14; 5; Partnership Agreements, Project Monitoring Reports, Web-sites of Project Promoters and their Partners. PA02 - Biodiversity and ecosystem services. Outcome: Avoided fragmentation of ecosystems. Outcome indicator; 2013; 2014; 2015; Total. Measures reducing fragmentation of landscape and animal population created and/or implemented, including eco-innovation measures; 0; 0; 0; 0; 0; 1; Programme Completion Report published at the website of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the Ministry of the Environment. Web site of the beneficiaries. Output: Ecosystems status analysed and monitored. Number of surveys, analyses or application studies focused on status or threats of the landscape, biodiversity and their protection/conservation created; 0; 0; 0; 0; 0; 3; Programme Completion Report published at the website of the Ministry of the Environment. Project and programme final reports. Website of the Ministry of the Environment and other relevant stakeholders.. Web site of the beneficiaries. Output: Habitats/ecosystems established, restored or improved. Number of implemented measures decreasing threats and fragmentation (green bridges, powerline protection etc.) and increasing habitats/ecosystems resilience and stability; 0; 0; 0; 9; 9; 3; Programme Completion Report published at the website of the Ministry of the Environment. Project and programme final reports.Website of the Ministry of the Environment and other relevant stakeholders.. Web site of the beneficiaries. Outcome: Improved integration of biodiversity considerations in sectoral policies and legislation. Outcome indicator; 2013; 2014; 2015; Total. Measures of the national biodiversity and nature protection strategies implemented, including eco-innovation measures; 0; 0; 0; 0; 0; 1; Programme Completion Report published at the website of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the Ministry of the Environment. Web site of the beneficiaries. Output: Implementation of action and management plans for endangered species enhanced. Number of action and management plans for endangered species created or implemented within the programme; 0; 0; 0; 0; 0; 6; Programme Completion Report published at the website of the Ministry of the Environment. Website of the Ministry of the Environment.Website of the beneficiaries. National and regional policy and strategic documents. Output: National biodiversity policy documents fulfilled with a special emphasis on collaboration with regional and local communities and NGOs implemented. Number of measures of national biodiversity policy documents implemented; 0; 0; 0; 0; 0; 2; Programme Completion Report published at the website of the Ministry of the Environment. Website of the Ministry of the Environment.Website of the beneficiaries. National and regional policy and strategic documents. Outcome: Increased awareness of and education in biodiversity and ecosystem services, including awareness of and education in the linkage between biodiversity and climate change, and economic valuation of ecosystems. Outcome indicator; 2013; 2014; 2015; Total. Measures for awareness of and education in biodiversity and ecosystem services created and/or implemented, including eco-innovation measures; 0; 0; 0; 0; 0; 1; Programme Completion Report published at the website of the Ministry of the Environment; Web site of the Ministry of the Environment; Web site of the beneficiaries; Evaluation of impact of awareness and educational activities (information feedback from implemented projects). Output: New environmental education programs and campaigns created and/or implemented. Number of environmental education programs and campaigns created and/or implemented; 0; 0; 0; 0; 0; 3; Programme Completion Report published at the website of the Ministry of the Environment. Website of the Ministry of the Environment.Website of the beneficiaries. Evaluation of impact of awareness and educational activities (information feedback from implemented projects). Output: New interpretative infrastructure created. Number of localities with the newly created interpretative infrastructure; 0; 0; 0; 0; 0; 3; Programme Completion Report published at the website of the Ministry of the Environment. Website of the Ministry of the Environment. Web site of the beneficiaries. Evaluation of impact of awareness and educational activities (information feedback from implemented projects). Outcome: Increased capacity to manage and monitor Natura 2000 sites effectively. Outcome indicator; 2013; 2014; 2015; Total. Increased capacity of Natura 2000 areas administration and monitoring; 0; 0; 0; 0; 0; 1; Programme Completion Report. Web site of the Ministry of the Environment. Web site of the beneficiaries. Output: Data from species and/or habitats monitoring are available and used for evaluation and reporting. Number of Natura 2000 sites (or mapping grids/plots) monitored within the Programme; 0; 0; 0; 77; 77; 8; Programme Completion Report published at the website of the Ministry for the Environment. Web site of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the beneficiaries. Output: Implementation of management plans measures intensified. Number of measures implemented; 0; 0; 0; 0; 0; 24; Programme Completion Report published at the website of the Ministry for the Environment. Web site of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the beneficiaries. PA03 - Environmental monitoring and integrated planning and control. Outcome: Improved environmental information on impact, status and trends. Outcome indicator; 2013; 2014; 2015; Total. Measures to promote open access to environmental information for the public and environmental NGOs created and/or implemented, including eco-innovation measures; 0; 0; 0; 0; 0; 1; Programme Completion Report published at the website of the Ministry of the Environment; Web site of the Ministry of the Environment; Web site of the beneficiaries; Data collected (Species Occurrence Database and of Nature Conservation Agency). Output: Environmental monitoring in geoparks intensified. Number of geoparks monitored; 0; 0; 0; 0; 0; 2; Programme Completion Report published at the website of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the Ministry of the Environment. Web site of the beneficiaries. Output: Implementation of environmental monitoring programmes enhanced. Number of surveys or studies on impacts, status and trends of the environment and its components created; 0; 0; 0; 2; 2; 3; Programme Completion Report published at the website of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the Ministry of the Environment. Web site of the beneficiaries. PA07 - Adaptation to climate change. Outcome: Developed strategies and measures for adapting to a changing climate. Outcome indicator; 2013; 2014; 2015; Total. Adaptation measures and strategies developed and/or implemented; 0; 0; 0; 0; 0; 1; Projects and programme final reports; Web pages of the Ministry the of Environment and other relevant stakeholders; Web pages of the European Environmental Agency and the EU Clearinghouse Mechanism on Adaptation. Output: New adaptation measures and strategies on climate change impacts developed. Number of vulnerability impact assessments, costs and benefits analysis, strategies and adaptation measures created, including e.g. eco-innovation measures.; 0; 0; 0; 1; 1; 5; Programme Completion Report. Project and programme final reports.Website of the Ministry of the Environment and other relevant stakeholders. Web site of the beneficiaries. Web pages of the European Environmental Agency and the EU Clearinghouse Mechanism on Adaptation. Output: New adaptation measures and strategies on climate change impacts implemented. Number of vulnerability impact assessments, costs and benefits analysis, strategies and adaptation measures implemented, including e.g. eco-innovation measures.; 0; 0; 0; 0; 0; 5; Programme Completion Report. Project and programme final reports. Website of the Ministry of the Environment and other relevant stakeholders. Web site of the beneficiaries. Web pages of the European Environmental Agency and the EU Clearinghouse Mechanism on Adaptation. Outcome: Developed systems for information exchange on climate change adaptation. Outcome indicator; 2013; 2014; 2015; Total. Systems for information exchange on climate change impacts and adaptation developed and/or implemented; 0; 0; 0; 0; 0; 1; Programme Completion Report published at the website of the Ministry of the Environment. Data collected (Species Occurrence Database and GIS Database Nature Conservation Agency). Web site of the Ministry of the Environment. Web site of the beneficiaries. Output: New systems for information exchange on climate change impacts and adaptation developed. Number of web databases, awareness raising campaigns, workshops/conferences, surveys, monitoring systems on climate change impacts and adaptation developed; 0; 0; 0; 9; 9; 3; Programme Completion Report. Project and programme final reports.Website of the Ministry of the Environment and other relevant stakeholders. Website of the beneficiaries. Web pages of the European Environmental Agency and the EU Clearinghouse Mechanism on Adaptation. Output: New systems for information exchange on climate change impacts and adaptation implemented. Number of web databases, awareness raising campaigns, workshops/conferences, surveys, monitoring systems on climate change impacts and adaptation implemented; 0; 0; 0; 0; 0; 3; Programme Completion Report. Project and programme final reports.Website of the Ministry of the Environment and other relevant stakeholders. Web site of the beneficiaries. Web pages of the European Environmental Agency and the EU Clearinghouse Mechanism on Adaptation.... |
| --- |
| CZ03: Funds for Non-governmental Organisations.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of men involved in exchange visits between beneficiary and donor states; 0; 0; 0; 9; 9; 15; Final reports of micro grants and of projects with component of bilateral cooperation. Number of organisations able to evidence good governance and management procedures; 58; 0; 0; 0; 89; Self-assessment questionnaire- at the beginning and end of project. Monitoring visits at the site of Project promoters, Monitoring Reports Final Reports. Number of organisations demonstrating to have robust financial procedures in place and diversify their funding sources; 45; 0; 0; 0; 76; Self-assessment questionnaire- at the beginning and end of project. Monitoring visits at the site of Project promoters, Monitoring Reports Final Reports. Number of organisations regularly consulting with users, beneficiaries and other stakeholders; 54; 0; 0; 0; 85; Self-assessment questionnaire- at the beginning and end of project. Monitoring visits at the site of Project promoters, Monitoring Reports Final Reports. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 41; 41; 8; Project partnership agreements – Final reports of micro grants, Project proposals with component of bilateral cooperation. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; Project Reports. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 0; 0; 0; Project Reports. Number of women involved in exchange visits between beneficiary and donor states; 0; 0; 0; 21; 21; 15; Final reports of micro grants and of projects with component of bilateral cooperation. PA10 - Funds for non-governmental organisations. Outcome: Active citizenship fostered. Outcome indicator; 2013; 2014; 2015; Total. Evidence of decision-makers responding to citizens actions; 0; 0; 0; 0; 0; 10; Reports on Implementation of the Aarhus Convention in the Czech Republic www.ucastverejnosti.cz. Number of laws, policies and practices changed or improved as a consequence of NGO advocacy activities; 0; 0; 0; 0; 0; 10; Parliamentary Press Releases, Media Monitoring. Number of mechanisms fostering dialogue between citizens, civil society and local/national institutions; 0; 0; 0; 56; 56; 15; Reports on Implementation of the Aarhus Convention in the Czech Republic www.ucastverejnosti.cz. Number of NGO networks/platforms/coalitions; 0; 0; 0; 42; 42; 20; Government Council for NGOs Reports. Number of NGOs reporting strengthened capacities (self assessment); 0; 0; 0; 0; 0; 85; Project Reports, Self-assessment Reports, Media Monitoring. Number of persons engaged on a regular basis in volunteering with civil society organisations; 0; 0; 0; 148; 148; 100; Statistical Surveys on Volunteering (Czech Statistical Office), Report on Volunteering in the Czech Republic (Hestia), USAID Civil Society Index. Output: Advocacy, watchdog and monitoring activities and anti-corruption measures supported. Number of advocacy activities and anti-corruption measures; 0; 0; 0; 48; 48; 70; Final project reports including case studies, press monitoring (Measures: Advocacy, watchdog and monitoring activities). Output: Capacity of Project Promoters strengthened. Number of Project Promoters able to evidence strengthened capacity in area of organizational management, multisource financing and planning and increased expertise; 0; 0; 0; 12; 12; 20; Final project reports; Entry/Final Self-Assessment Reports (Measures: capacity-building). Output: Mechanisms created to foster dialogue between citizens, civil society and public administration. Number of mechanisms fostering dialogue between citizens, civil society and public administration; 0; 0; 0; 56; 56; 50; Final project reports including PR printouts, press monitoring (Measures: watchdog and advocacy activities). Output: NGO coalitions and networks in place to build partnerships with state administration, commercial sector and academia. Number of coalitions / platforms / networks in place; 0; 0; 0; 42; 42; 40; Final project reports including coalitions case studies, press monitoring; statistic of settled coalitions (Measures: networking and advocacy activities). Output: NGO professionalism improved. Number of system activities supported aiming to improve NGO professionalism; 0; 0; 0; 8; 8; 15; Final project reports including lists of participants, PR printouts, photo documentation (Measures: capacity-building activities). Output: Volunteering in the Czech Republic further developed through NGO initiatives. Number of Initiatives developed to support volunteering; 0; 0; 0; 8; 8; 15; Final project reports including PR printouts, press monitoring (Measures: raising-awareness). Outcome: Democratic values, including human rights, promoted. Outcome indicator; 2013; 2014; 2015; Total. Number of NGOs informed and involved in combating racism and xenophobia (including hate speech and hate crimes); 0; 0; 0; 56; 56; 95; Report on the State of Human Rights in the Czech Republic, Social Watch: Gender Equity Index, National Action Plan on Violence Against Women, Project Monitoring Reports. Number of NGOs promoting democratic values, including human rights; 0; 0; 0; 56; 56; 70; Report on the State of Human Rights in the Czech Republic, Social Watch: Gender Equity Index, National Action Plan on Violence Against Women, Project Monitoring Reports. Numbers of NGOs committed to NGO Codes of Practice and ethics; 0; 0; 0; 20; 20; 20; Project Monitoring Reports. Output: Capacity of Project Promoters strengthened. Number of Project Promoters able to evidence strengthened capacity in area of organizational management, multisource financing and planning and increased expertise; 0; 0; 0; 15; 15; 30; Final project reports; Entry/Final Self-Assessment Reports (Measures: capacity-building). Output: Individuals, whose human rights are being violated or are discriminated, received improved support from NGOs. Number of Individuals; 0; 0; 0; 1787; 1787; 600; Final project reports including individual case studies and statistic of supported individuals (Measures: social services, watchdog and advocacy activities). Output: More women are involved in decision-making and take leadership positions. Number of activities that support women to get more involved in decision-making and take leadership positions; 0; 0; 0; 22; 22; 20; Final project reports including case studies, press monitoring, photo documentation (Measures: raising-awareness and advocacy activities). Output: National motivation and information campaign to support democratic values and human rights protection implemented (targeting horizontal concerns). Number of information materials developed and distributed; 0; 0; 0; 18; 18; 50; Final project reports including PR printouts, information materials, press monitoring (Measures: raising awareness). Number of supported campaigns targeting horizontal concerns; 0; 0; 0; 54; 54; 15; Final project reports including PR printouts, information materials, press monitoring (Measures: raising awareness). Outcome: Empowerment of vulnerable groups. Outcome indicator; 2013; 2014; 2015; Total. Number of beneficiaries engaged in the strategic planning/implementation of activities; 0; 0; 0; 0; 0; 325; National Action Plan on Social Inclusion, Strategy for Combating Social Exclusion, Report on the State of the Roma Minority (Office of the Government of the Czech Republic). Number of NGOs using participatory approaches to engage vulnerable groups; 0; 0; 0; 0; 0; 25; National Action Plan on Social Inclusion, Strategy for Combating Social Exclusion, Report on the State of the Roma Minority (Office of the Government of the Czech Republic). Output: Capacity of Project Promoters strengthened. Number of Project Promoters able to evidence strengthened capacity in area of organizational management, multisource financing and planning and increased expertise; 0; 0; 0; 8; 8; 7; Final project reports; Entry/Final Self-Assessment Reports (Measures: capacity-building). Output: Increased cooperation among NGOs, schools and counseling centres to ensure the best interest of children and youth, including the development of methodologies to facilitate inclusive education. Number of developed functional cooperations among NGOs, schools and counseling centres; 0; 0; 0; 107; 107; 30; Final project reports including cooperation's case studies; statistic of settled cooperation (Measures: advocacy and networking). Number of methodologies developed to ensure the best interest of Roma children and youth; 0; 0; 0; 1; 1; 10; Final project reports including cooperation's case studies; statistic of settled cooperation (Measures: advocacy and networking). Output: Roma children and youth included in educational and leisure activities. Number of leisure and educational activities organised where Roma children and youth are included; 0; 0; 0; 222; 222; 12; Final project reports including internal statistics, individual case studies, photo documentation, information materials, press monitoring (Measures: educational activities). Number of Roma children and youth included; 0; 0; 0; 1688; 1688; 350; Final project reports including internal statistics, individual case studies, photo documentation, information materials, press monitoring (Measures: educational activities). Outcome: Increased contribution to sustainable development achieved. Outcome indicator; 2013; 2014; 2015; Total. Number of NGOs supported to focus on sustainable development, conservation of biodiversity and climate protection; 0; 0; 0; 43; 43; 32; State of the Environment Reports, Statistical Environmental Yearbooks. Number of NGOs supported to raise awareness and involve the target groups in the field of sustainable development, conservation of biodiversity and climate protection; 0; 0; 0; 43; 43; 22; State of the Environment Reports, Statistical Environmental Yearbooks. Output: Number of NGOs able to evidence strengthened capacity. Strengthened capacity of NGOs in following areas: organizational management, multisource financing and planning and increased expertise; 0; 0; 0; 22; 22; 12; Final project reports; Entry/Final Self-Assessment Reports (Measures: capacity-building). Output: Practical measures implemented in conservation of biodiversity and climate protection. Number of natural valuable locations influenced by implementation of projects focusing on conservation of biodiversity and climate protection; 0; 0; 0; 86; 86; 17; Final project reports including photo documentation (Measures: services). Output: Target groups better informed about the importance of sustainable development, conservation of biodiversity and climate protection. Number of mechanisms (campaigns, educational activities, community actions) fostering interest of target groups in conservation of biodiversity, climate protection and sustainable environment; 0; 0; 0; 1349; 1349; 30; Final project reports including PR printouts, information materials, press monitoring and photo documentation (Measures: raising awareness). Outcome: Provision of welfare and basic services to defined target groups increased. Outcome indicator; 2013; 2014; 2015; Total. Established cooperation among NGOs, authorities and experts for social and legal protection of children (complex approach to the target group); 0; 0; 0; 0; 0; 25; National Strategy to Protect, Children's Rights aka the “Right to Childhood” (Government Strategic Document); Strategic documents on regional level (Action Plans on Services). Number of basic and welfare services that meet needs of defined target groups; 0; 0; 0; 50; 50; 30; National Strategy to Protect, Children's Rights aka the “Right to Childhood” (Government Strategic Document). Output: Capacity of Project Promoters strengthened. Number of Project Promoters able to evidence strengthened capacity in area of organizational management, multisource financing and planning and increased expertise; 0; 0; 0; 24; 24; 10; Final project reports; Entry/Final Self- Assessment Reports (Measures: capacity-building). Output: Cooperation among NGOs, authorities and experts for social and legal protection of children on local or regional level developed or enhanced. Number of cooperations established or strengthened; 0; 0; 0; 134; 134; 20; Final project reports including cooperations' case studies; statistic of settled cooperation (Measures: advocacy and networking). Output: Information on available services (including free hotlines) for dealing with various life situations shared with the public/spread to the public or known among the public. Number of activities to spread information on available services; 0; 0; 0; 13; 13; 15; Final project reports including PR printouts, information materials, press monitoring (Measures: raising-awareness). Output: Services for children and youth (including Roma) with disabilities or social disadvantages improved and available. Number of children and youth with disabilities or social disadvantages with access to improved services; 0; 0; 0; 2274; 2274; 1,000; Final project reports including methodologies of improved services; Final project reports including internal statistics, individual case studies, photo documentation (Measures: social services). Number of services for children and youth (including Roma) with disabilities or social disadvantages; 0; 0; 0; 50; 50; 30; Final project reports including methodologies of improved services; Final project reports including internal statistics, individual case studies, photo documentation (Measures: social services).... |  |

CZ04: Children and Youth at Risk.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of new policies, laws and regulations adapted, as a result of bilateral cooperation, under the grants; 0; 0; 0; 0; 0; 1; New draft Act on Protection of the Rights of Children, Support for Families and Foster Care prepared and submitted for approval.. Number of project partnership agreements in beneficiary civil society; 0; 0; 1; 1; 2; 0; N/a. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; N/a. Number of project partnership agreements in the beneficiary public sector; 0; 0; 1; 0; 1; 1; Partnership Agreement between the Barne-, ungdoms- og familiedirektoratet (Norway) and the Ministry of Labour and Social Affairs (Czech Republic) as anticipated in the PDP.. PA11 - Children and youth at risk. Outcome: Effective and efficient measures addressing vulnerable groups of children and youth facing particular risks implemented. Outcome indicator; 2013; 2014; 2015; Total. Measures addressing the needs of vulnerable groups of children, youth and families facing particular risks created; 0; 0; 0; 0; 0; 1; Reports on progress of transformation, register of service providers and register of issued authorizations providing social and legal protection. Output: Transformation plans focusing on needs of vulnerable groups of children, youth and families elaborated. Number of transformation plans of institutions (substitute solution, schedule, budget, educational needs, monitoring and evaluation mechanisms).; 0; 0; 0; 0; 10; Transformation plans prepared and submitted by the OC beneficiaries. Reports (minutes) from Regional and municipal meetings. Output: Conditions for coordination of transformation of residential facilities into an effective network of services providing care for children in need and families created. Number of methodologies for the creation and implementation of transformation plans for residential institutions; 0; 0; 0; 1; 1; 1; Methodology for creation and implementation of transformation plans prepared and shared with the OC beneficiaries. Outcome: Laws, policies and measures in the field of children’s and youth rights, as enshrined in relevant international instruments effectively implemented. Outcome indicator; 2013; 2014; 2015; Total. Newly developed and/or enforced child-centred legislation in line with the recommendations of the UN Committee and other documents; 0; 0; 0; 0; 0; 2; Collection of Laws of the Czech Republic. Number of laws, policies and practices developed/improved as a consequence of stakeholders' actions; 0; 0; 0; 0; 0; 1; Prepared implementing scheme, interim reports, reports on results. Output: Implementation of the new legislation as well as the implementing tools prepared. Number of information and media campaign of the new legislation; 0; 0; 0; 0; 0; 2; Reports from the supplier, including detailed information on the extent as well as content of the campaign(s). Outputs of the campaigns (samples, brochures, TV spots, press articles, etc.). Number of local authorities and experts in charge of implementation of the new legislation educated and trained; 0; 0; 0; 0; 0; 3,000; Reports from educational/training events, list of participants to the educational/training events. Number of methodologies and procedures for the new legislation; 0; 0; 1; 0; 1; 10; Written methodologies and procedures prepared and published/distributed. Number of new legislation timely prepared and submitted for individual phases of the legislative process; 0; 0; 0; 0; 0; 1; Reports and other relevant written outputs from separate stages of legislative process. Output: Samples of good practices between the Main Project Partner and the Project Partner as well as the transfer of experience among the key national stakeholders exchanged. Number of coordination meetings; 0; 0; 1; 1; 2; 6; Reports (or minutes) from the co-ordination meetings. Number of expert opinions; 0; 0; 8; 22; 30; 30; Expert opinions submitted and filed. Number of national expert seminars; 0; 0; 0; 1; 1; 1; Report from national expert seminar, list of participants, contracts with the experts. Outcome: Quality of child welfare systems and protection measures effectively improved, relaying the views of relevant stakeholders and society at large through high quality and participatory debate. Outcome indicator; 2013; 2014; 2015; Total. Consultative mechanism involving children, youth, families and other stakeholders established and operational; 0; 0; 0; 1; 1; 1; Implemented projects, monitoring reports. Consultative mechanism involving children, youth, families and other stakeholders established and operational; 0; 0; 0; 0; 0; 2; Implemented projects, monitoring reports. Output: Awareness regarding the rights of the child through local or nation-wide activities raised. Number of activities, whether local or nation-wide, aimed at raising awareness about children's rights; 0; 0; 0; 1; 1; 3; At least three activities supported as part of the SGS. Monitoring reports from the activities as well as other outputs (photos, press articles, TV spots etc.). Output: Systems and measures for protection of children and young people supported. Number of tools and procedures (methodologies) elaborated on the basis of supported projects for the effective determining of children´ opinion and its involvement in various types of decision-making processes including number of trainings for employees of relevant institutions in this area; 0; 0; 0; 1; 1; 3; Written methodologies prepared and timely submitted, reports from the educational/training events, including list of participants....

CZ05: National, Regional, Local Initiatives to Reduce Inter-Group Inequalities and to Promote Social Inclusion.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 0; 0; 0; n/a. PA12 - Local and regional initiatives to reduce national inequalities and to promote social inclusion (EEA grants). Outcome: Local and regional authorities, as well as private and civil society actors, are developing initiatives to strengthen anti-discriminatory measures for groups vulnerable to social and economic exclusion. Outcome indicator; 2013; 2014; 2015; Total. Capacity building and transfer of good practice in local and regional schools and authorities in regions facing and dangers of racism and hate crimes; 0; 0; 0; 0; 0; 100; Project documentation, attendance sheets. Increased public awareness of issues of hate violence through campaign against racism and hate crimes; 0; 0; 0; 0; 0; 20; Project evaluation - i.e. opinion study before and after campaign realization. Output: Exchange of best practice on the international, national and regional level. International workshop / conference; 0; 0; 0; 0; 0; 1; At least one workshop or conference with the participation of foreign experts from donor states is planned within the Programme. Number of created special webpages; 0; 0; 1; 0; 1; 2; (1) Specially developed webpages will be created within the campaign Against Racism and Hate Violence and (2) webpages focused on local municipalities with the goal of spreading good practice of inclusive policies.. Output: Increase of awareness regarding social risks of extremism and racism by educational activities and support for implementation of pro-inclusive measures.. Number of local actors in the Ustecky a Moravskoslezsky region trained in the processes how to face the racism and hate violence; 0; 0; 0; 0; 0; 650; New didactic materials will be created within the program and 650 local actors in the Ustecky and Moravskoslezsky regions will be trained how to face the racism and manifestations of hate violence, how to impede them including readiness to act against activities leading to violence and how to pass pro-inclusive attitudes as efficiently as possible.. Number of school with deeper cooperation and supervision; 0; 0; 0; 0; 0; 10; More intensive cooperation in 10 schools in places with socially excluded localities is expected, schools will be selected on the basis of an inquiry about interest and willingness to commitment in promoting systematic measures, preferentially in places, where the Agency for Social Inclusion is operational.. Output: The research of new forms of moneylending and migration in socially excluded localities will provide new information on how to combat these phenomena.. Number of researches conducted in socially excluded localities; 0; 0; 0; 0; 0; 2; 2 extensive researches will be concluded within the program. Their topics will be the current forms of moneylending and migration in socially excluded localities.. Output: Young people aged 15 - 25 will be informed via the nationwide media campaign about manifestations of racism and hate violence as well as about means of how to face them with personal attitudes and by supporting the inclusive policies. Number of video spots aimed at young people under 25, aired nationwide; 0; 0; 536; 252; 788; 200; Realization of the nationwide media campaign Against Racism and Hate Violence according to a predefined schedule. At least 200 video spots aimed at young people under 25 will be aired nationwide....

CZ06: Cultural Heritage and Contemporary Arts.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 10; 5; 15; 0; Not applicable. Number of project partnership agreements in the beneficiary private sector; 0; 0; 5; 7; 12; 0; Not applicable. Number of project partnership agreements in the beneficiary public sector; 0; 0; 9; 3; 12; 0; Not applicable. PA16 - Conservation and revitalisation of cultural and natural heritage. Outcome: Cultural heritage restored, renovated and protected. Outcome indicator; 2013; 2014; 2015; Total. Number of actions taken to preserve movable cultural heritage and written cultural heritage; 0; 0; 0; 0; 0; 2; project reporting, on-site monitoring, annual programme evaluation. Number of buildings of cultural heritage value and buildings used for museum-type collections restored or rehabilitated; 0; 0; 0; 0; 0; 13; project reporting, on-site monitoring, annual programme evaluation. Number of restored and digitalized cinematographic works; 1; 0; 0; 0; 0; 11; project reporting, on-site monitoring, annual programme evaluation. Output: Cinematographic works restored and digitalised. Number of restored and digitalized cinematographic works; 4; 0; 0; 0; 0; 14; project reporting, on-site monitoring, annual programme evaluation. Output: Collections including libraries collections restored; optimal environment for museums, libraries, archives and written cultural heritage created. Number of actions taken to preserve movable cultural heritage and written cultural heritage; 0; 0; 0; 0; 0; 2; project reporting, on-site monitoring, annual programme evaluation. Output: National cultural heritage sites, cultural heritage sites, UNESCO heritage sites and buildings used for museum-type collections renovated or repaired. Number of buildings of cultural heritage value and buildings used for museum-type collections restored or rehabilitated; 0; 0; 0; 0; 0; 12; project reporting, on-site monitoring, annual programme evaluation. PA17 - Promotion of diversity in culture and arts within European cultural heritage. Outcome: Contemporary art and culture presented and reaching a broader audience. Outcome indicator; 2013; 2014; 2015; Total. Number of new cultural performances, interdisciplinary and exhibition projects, concert events in the area of theatre, visual, music and film art; 0; 0; 0; 0; 0; 4; project reporting, on-site monitoring, annual programme evaluation. Output: Creative workshops in the area of theatre, music, visual and film art held. Number of creative workshops (specialized courses, conferences, seminars); 0; 0; 0; 0; 0; 4; project reporting, on-site monitoring, annual programme evaluation. Output: New performance projects supported. Number of new cultural performances, interdisciplinary and exhibition projects, concert events in the area of theatre, visual and music and film art; 0; 0; 0; 0; 0; 4; project reporting, on-site monitoring, annual programme evaluation....

CZ07: EEA Scholarship Programme; Bilateral Scholarship Programme.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; NA. Number of project partnership agreements in the beneficiary private sector; 0; 0; 1; 1; 2; 0; NA. Number of project partnership agreements in the beneficiary public sector; 0; 0; 4; 38; 42; 12; National Agency's list of realized projects. PA19 - Scholarships. Outcome: Increased and strengthened institutional cooperation at all levels of the education sector (school education, higher education, vocational training/education and adult education) between Beneficiary and EEA EFTA States. Outcome indicator; 2013; 2014; 2015; Total. Evidence of forecasted/future cooperation; 0; 0; 0; 0; 0; 3; National Agency's statistics. Joint products and services; 41; 0; 0; 0; 0; 7; National Agency's statistics. Output: Joint projects identified and implemented by partner institutions. Number of bilateral partnership agreements; 0; 0; 0; 0; 0; 2; National Agency's statistics. Number of projects; 41; 0; 0; 0; 0; 7; National Agency's statistics. Output: Mobility programme for institutional cooperation effectively implemented. Number of institutional cooperation project applications received by PO; 63; 0; 2; 9; 11; 9; National Agency's statistics. Number of promotional events where EEA/Norway Grants scholarship programme was presented; 0; 0; 11; 15; 26; 19; National Agency's statistics. Outcome: Increased higher education student and staff mobility between Beneficiary and EEA EFTA States. Outcome indicator; 2013; 2014; 2015; Total. Enhanced competence of HE sector staff as a result of international mobility; 41; 0; 0; 8; 8; 2; National Agency's statistics. Number of PhD students that were preparing and/or presented PhD thesis; 43; 0; 0; 1; 1; 3; National Agency's statistics. Number of students with received ECTS credits; 497; 0; 0; 0; 0; 10; Baseline: Erasmus mobility statistics. Target: Erasmus mobility statistics + National Agency statistics. Output: Agreements for HE student and staff mobility formalized/existing agreements enhanced. Number of mobile students as part of new or existing mobility agreements; 0; 0; 0; 0; 0; 8; National Agency's statistics. Number of new HE mobility agreements; 0; 0; 0; 0; 0; 2; National Agency`s statistics. Output: HE mobility programme promoted effectively among institutions and beneficiaries selected on a competitive basis. Number of mobility project applications received by PO; 0; 0; 1; 6; 7; 8; National Agency`s statistics. Number of promotional events where EEA/Norway Grants scholarship programme was presented; 0; 0; 11; 15; 26; 15; National Agency`s statistics. Including promotional events conducted by project promoters. PA24 - Bilateral scholarship programme. Outcome: Increased and strengthened institutional cooperation within the higher education sector between the Beneficiary States and Norway. Outcome indicator; 2013; 2014; 2015; Total. Joint products and services; 41; 0; 0; 0; 0; 38; National Agency's statistics. Output: Joint projects identified and implemented by partner institutions. Number of bilateral partnership agreements; 0; 0; 0; 0; 0; 10; National Agency's statistics. Number of projects; 41; 0; 0; 0; 0; 31; National Agency's statistics. Output: Mobility programme for institutional cooperation effectively implemented. Number of institutional cooperation project applications received by PO; 63; 0; 11; 38; 49; 42; National Agency's statistics. Number of promotional events where EEA/NRW Grants scholarship programme was presented.; 0; 0; 11; 15; 26; 68; National Agency's statistics. Outcome: Increased higher education student and staff mobility between Beneficiary States and Norway. Outcome indicator; 2013; 2014; 2015; Total. Enhanced competence of HE sector staff as a result of international mobility; 41; 0; 0; 25; 25; 47; National Agency's statistics. Number of PhD students that were preparing and/or presented PhD thesis; 43; 0; 0; 13; 13; 47; National Agency's statistics. Number of students with received ECTS credits; 497; 0; 0; 23; 23; 80; Baseline: Erasmus mobility statistics. Target: Erasmus mobility statistics + National agency's statistics. Output: Agreements for HE student and staff mobility formalized / existing agreements enhanced. Number of mobile students as part of new or existing mobility agreements; 0; 0; 0; 0; 0; 90; National Agency's statistics. Number of new HE Mobility Agreements; 0; 0; 0; 0; 0; 8; National Agency's statistics. Output: HE mobility programme promoted effectively among institutions and beneficiaries selected on a competitive basis. Number of mobility project applications received by PO; 0; 0; 10; 22; 32; 36; National Agency's statistics. Number of promotional events where EEA/NRW Grants scholarship programme was presented; 0; 0; 11; 15; 26; 54; National Agency's statistics....

CZ08: Pilot studies and surveys on CCS technology.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; Not relevant. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; Not relevant. Number of project partnership agreements in the beneficiary public sector; 0; 0; 3; 3; 1; - Partnership Agreements - Project Monitoring Reports - Web sites of Project Promoters and their Partners. Number of projects with expected shared results (both partners are involved professionally in planning and implementation and can claim credit for achieved results); 0; 0; 3; 3; 1; - Partnership Agreements - Project Monitoring Reports - Web sites of Project Promoters and their Partners. Number of women involved in exchange visits between beneficiary and donor states; 0; 0; 4; 4; 2; by counting. PA20 - Carbon capture and storage (CCS). Outcome: Increased knowledge and transnational cooperation on CCS. Outcome indicator; 2014; 2015; Total. Availability of documentation, data and information allowing a decision to be made on the practical use, capture and storage of CO2 in accordance with the Directive on CCS; 0; 0; 0; 0; 1; websites of the MoE and its partners, links to sources for project investigators; - CCS archives, administered by the MoE; final programme report. Increased awareness among the general and professional public of CCS, improved knowledge and transnational cooperation in CCS; 0; 0; 0; 0; 1; Final programme report; qualified and on-going provision of information on CCS from the state and the public administration; scheme of conditions to improve cooperation between the state and the public administration, professional circles and the general public on CCS issues. Output: Completed surveys to explore the possibilities of the practical application of CCS technology in the Czech Republic, methods proposed for the capture, transport and storage of CO2. Number of analyses and studies for an assessment of the possibility of the practical application of CCS technology in the Czech Republic (including methods for the capture, transport and storage of carbon dioxide and related technological issues); 0; 0; 10; 10; 3; Monitoring and final project reports, completed analyses, studies and methods for the capture, storage and transport of CO2, records and reports on test drilling, tests, pilot operations, economic studies and legislative analyses. Output: Increased knowledge of staff working in the state and public administration and awareness of the general and professional public in CCS technologies. Number of awareness campaigns, events, methods and tools aimed at transferring information (seminars, conferences, workshops, pilot projects) and increasing awareness, transnational cooperation and on-going share of information in CCS (www, electronic channels, study tours); 0; 0; 18; 18; 5; Monitoring and final project reports, results of opinion polls, statistics and sociological surveys , records of events/campaigns run stored at organisers and their subsidiaries, records and proceedings of seminars, conferences, workshops, attendance sheets, reports from study tours, press reports and articles in the media, photographs, etc.....

CZ09: The Czech – Norwegian Research Programme.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; NA. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; NA. Number of project partnership agreements in the beneficiary public sector; 0; 0; 14; 2; 16; 0; NA. PA23 - Bilateral research cooperation. Outcome: Increased research cooperation between Norway and the Beneficiary States. Outcome indicator; 2013; 2014; 2015; Total. Number of research institutions cooperating within the programme; 0; 0; 57; 7; 64; 50; List of approved applications and final reports.. Output: International research cooperation projects. Number of cooperation projects; 0; 0; 18; 5; 23; 40; The output of the provided outcome is the international research cooperation itself. Any further specific outputs will help to prove the outcome.. Output: Internationally refreed(joint) scientific publications published as a part of the programme. Number of internationally refereed (joint) scientific publications; 0; 0; 3; 50; 53; 40; The evaluations of biblimoteric data is suitable and often use method.. Output: Suitable conditions and enviroment for young researchers. Number of female researchers involved; 0; 0; 107; 72; 179; 20; Final reports. Bilateral science and research projects will comprise activities aimed at supporting young researchers (involvement of Ph.D. students in a project, involvement of researchers who have returned from maternity leave, promotion of mobility not only of young researchers closely linked to the project, etc.).. Number of PhD students and postdocs involved; 0; 0; 94; 59; 153; 20; Final reports. Bilateral science and research projects will comprise activities aimed at supporting young researchers (involvement of Ph.D. students in a project, involvement of researchers who have returned from maternity leave, promotion of mobility not only of young researchers closely linked to the project, etc.).....

CZ10: Capacity-building and Institutional Cooperation between Benificiary State and Norwegian Public Institutions, Local and Regional Authorities.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2014; 2015; Total. Number of articles published in one country about the other partner country; 0; 0; 2; 2; 2; Media monitoring. Number of men involved in exchange visits between beneficiary and donor states; 0; 0; 9; 9; 6; Travel reports, travel records, joint output/materials etc.. Number of new policies, laws and regulations adapted, as a result of bilateral cooperation, under the grants; 0; 0; 1; 1; 2; New draft Act and policies and regulations. Number of new technologies/new practises, including IT-systems, adopted in a beneficiary state, as a result of transfer of knowledge from a donor state partner; 0; 0; 0; 0; 2; Protocol of implementation and real operation. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; Not Applicable. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; Not Applicable. Number of project partnership agreements in the beneficiary public sector; 0; 0; 1; 1; 2; Partnership agreements signed by both project partners.. Number of projects with expected shared results (both partners are involved professionally in planning and implementation and can claim credit for achieved results); 0; 1; 0; 1; 2; Monitroing yearly and final reports of individual PDP and the entire PRG; Attendance sheets for particular events, minutes from meetings, reports from official trips, shared documents. Number of women involved in exchange visits between beneficiary and donor states; 0; 0; 6; 6; 4; Travel reports, travel records, joint output/materials etc.. PA25 - Capacity-building and Institutional Cooperation between Beneficiary State and Norwegian Public Institutions, Local and Regional Authorities. Outcome: Enhanced capacity and quality of the services provided by public institutions, local and regional authorities through enhanced institutional capacity and human resources development. Outcome indicator; 2014; 2015; Total. Increasing the number of in-depth investigation (cases); 200; 0; 0; 0; 400; Annual report of the project. Increasing the number of sources of information (sources); 3; 0; 0; 0; 5; Annual report of the project. Increasing the number of users; 0; 0; 0; 0; 30; Annual report of the project. Number of institutions with strengthened capacity; 0; 0; 0; 0; 2; Financial Analytical Unit, Ministry of Finance Unit for Uncovering Corruption and Financial Crime, Police of the Czech Republic. Shortening the average time solving cases (months); 2; 0; 0; 0; 1; Annual report of the project. Output: Increased effectiveness and efficiency of Czech institutions in combating corruption.. Number of state officials, police officers, judges, state prosecutors, etc trained in preventing and combating corruption, identifying and pursuing corruption-related proceeds; 0; 100; 183; 283; 350; Project documentation, lists of presentations, lists of participants, interim reports, final report. Number of trained staff with strengthened technical capacity; 0; 0; 0; 0; 30; List of trained users, number of users with certification, programme reports. Output: Increased knowledge of anti-corruption practices. Number of delivered studies or comparative analyses of legislative environment; 0; 0; 3; 3; 3; Adoption of studies. Output: Increased publicity for anti-corruption measures. Number of publicity measures; 0; 1; 2; 3; 4; Programme reports. Output: Software programme for data-mining delivered. Number of software programmes delivered; 0; 0; 0; 0; 1; Programme reports. Percentage of cases with in-depth analysis; 30; 0; 30; 30; 60; Programme reports. The average time (in months) for investigation of a case; 3; 0; 3; 3; 2; Programme reports....

CZ11: Public Health Initiatives.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 2; 2; 8; Number of partnership agreements. Number of projects with expected shared results (both partners are involved professionally in planning and implementation and can claim credit for achieved results); 0; 0; 0; 2; 2; 10; Number of projects expected shared results supported by programme. PA27 - Public health initiatives (Norway grant). Outcome: Improved access to and quality of health services including reproductive and preventive child health care. Outcome indicator; 2013; 2014; 2015; Total. Number of activities leading to both the improvement of diagnostics of rare diseases and the care for patients with rare diseases; 0; 0; 0; 8; 8; 7; The result of the Programme will be determined as the sum total of the reported activities of individual projects (PDP+SGS). Number of activities leading to the reduction of child injuries; 0; 0; 0; 1; 1; 2; Indicator will be identified by the completion of the Programme. Number of children benefiting from the improved preventive activities; 0; 0; 0; 3445; 3445; 200; Average annual utilization of preventive activities will be reported after completion of each project. The sum will indicate the fulfilment of the Programme as the whole. Output: Activities in the field of health care for children in the Czech Republic centralized. The number of established centres on the national level; 0; 0; 0; 0; 0; 2; Project report. Output: NGO activities in the field of care for children (injuriy prevention, prevention of after-effects of health problems and diseases in the child age and the area of care for patients with rare diseases developed. Number of NGO prevention programmes on child injuries, after-effects of diseases and health problem in child age and care for persons with rare diseases; 0; 0; 0; 0; 0; 15; Project report. Output: Primary and secondary prevention focused on reduction of after effects of diseases, injuries and health problems in child age developed. Number of programmes of primary and secondary prevention; 0; 0; 0; 10; 10; 10; Project report. Outcome: Improved mental health services. Outcome indicator; 2013; 2014; 2015; Total. Number of patients benefiting from the improved mental health services; 0; 0; 0; 152; 152; 300; Each medical facility (Programme’s recipients) will quantify the average annual utilization of the new system of rehabilitation based on their statistical methods. On the Programme level it will be the sum total of reported values.. Output: System of new approach to the rehabilitation of patients established. Number of created systems of new approach to rehabilitation of patients; 0; 0; 0; 0; 0; 1; Project report. Output: Comprehensive rehabilitation system in the mental hospitals implemented. Number of implemented systems securing the transition of activities from the institutions of psychiatric care to the new approach to the rehabilitation; 0; 0; 0; 3; 3; 15; Project report. Output: The development of NGO activities in the field of mentally ill patients focused on de-institutionalization and de-stigmatization. Number of programmes focused on de-institutialization and de-stigmatization created and implemented by NGOs; 0; 0; 0; 0; 0; 15; Project report....

CZ12: Mainstreaming Gender Equality and Promoting Work-Life Balance & Domestic and Gender-based Violence; Let’s give (wo)men a chance.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of articles published in one country about the other partner country; 0; 0; 0; 4; 4; 6; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of joint (bilateral) articles published, written by persons from both an institutions in a beneficiary and donor state, published in a national or international publications, originated from a project financed by the programme; 0; 0; 0; 7; 7; 12; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of men involved in exchange visits between beneficiary and donor states; 0; 0; 0; 4; 4; 5; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of new policies, laws and regulations adapted, as a result of bilateral cooperation, under the grants; 0; 0; 0; 0; 0; 4; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of professional networks between institutions in beneficiary and donor states established and operational; 0; 0; 0; 0; 0; 2; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 1; 1; 6; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; -. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 0; 0; 6; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of projects with expected shared results (both partners are involved professionally in planning and implementation and can claim credit for achieved results); 0; 0; 0; 0; 0; 5; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of women involved in exchange visits between beneficiary and donor states; 0; 0; 0; 6; 6; 20; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. PA28 - Mainstreaming gender equality and promoting work-life balance (Norway grant). Outcome: Awareness raised and research on gender issues promoted. Outcome indicator; 2013; 2014; 2015; Total. Attitudes towards gender roles (survey); 0; 0; 0; 9; 9; 10; +10% Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Number of publications, reports, scientific papers originting from projects financed by the Programme made available to public; 0; 0; 10; 10; 5; Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Output: Gender mainstreaming within education institutions improved. Number of activities aimed at elimination of gender segregation in education; 0; 0; 0; 6; 6; 10; Programme documentation. Number of teaching materials and curricula with incorporated gender perspective; 0; 0; 0; 1; 1; 5; Programme documentation. Output: Information campaigns executed and research on gender equality conducted/published. Number of campaigns, information events, including publication of printed materials related and their distribution, all related to gender equality; 0; 0; 0; 156; 156; 30; Programme documentation. Number of conducted/ published research/studies related to gender equality; 0; 0; 0; 15; 15; 10; Programme documentation. Outcome: Balance between work, private and family life improved. Outcome indicator; 2013; 2014; 2015; Total. Number of comprehensive and integrated policies, particularly employment policies, aimed at promoting work/life balance implemented; 0; 0; 0; 2; 2; 15; Monitoring undertaken by the Programme Promoter by the means of continuous and final reports of Project Promoters and the Programme Operator’s survey. Number of policies, laws and regulations adopted or revised; 0; 0; 4; 4; 5; Monitoring undertaken by the Programme Promoter by the means of continuous and final reports of Project Promoters and the Programme Operator’s survey. Provision of childcare services for children under the mandatory school age (measured as % of population offered childcare services as proportion of total population under the mandatory school age); 0; 0; 0; 5; 5; 5; +5% Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s survey (questionnaires) at the start and again at the end of the Programme implementation period.. Output: Flexible working time arrangements for employees introduced. Number of organisations that have introduced flexible working time arrangements for their employees / number of new co-working centres helping parents to return to employment; 0; 0; 0; 2; 2; 20; Programme documentation. Number of persons with a new flexible working time arrangement; 0; 0; 0; 0; 0; 50; Programme documentation. Output: Standard, corporate and alternative child-care facilities introduced. Number of newly started or maintained child-care facilities; 0; 0; 0; 7; 7; 10; Programme documentation. Outcome: Capacity of gender equality organisations and networks strengthened. Outcome indicator; 2013; 2014; 2015; Total. Number of institutions with strengthened capacity; 2; 0; 14; 14; 5; Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Number of networks / coalitions addressing gender equality in place; 2; 0; 0; 193; 193; 5; Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Output: Activity of existing coalitions or networks connecting gender organisations increased. Number of media outputs published during one year connected with gender equality carried out in cooperation with several organisations by the means of their network; 0; 0; 0; 760; 760; 10; Programme documentation. Number of new thematic projects in cooperation with several organisations or by the means of their networks created/realised; 0; 0; 0; 6; 6; 5; Programme documentation. Output: Strengthened capacities of individual organisations supporting gender equality. Number of gender equality organisations with improved capacity; 0; 0; 0; 14; 14; 20; Programme documentation. Number of launched or strengthened cooperation processes of gender organisations with research and educational institutions, companies, social partners, local governments, state administration, political parties, etc.; 0; 0; 0; 193; 193; 15; Programme documentation. Outcome: Gender issues across policies and practices mainstreamed. Outcome indicator; 2013; 2014; 2015; Total. Number of policies and practices that are gender-mainstreamed; 0; 0; 0; 13; 13; 20; Monitoring undertaken by the Programme Promoter by the means of continuous and final reports of Project Promoters and the Programme Operator’s survey. Number of policies, laws and regulations adopted or revised; 0; 0; 13; 13; 20; Monitoring undertaken by the Programme Promoter by the means of continuous and final reports of Project Promoters and the Programme Operator’s survey. Output: Gender-sensitive analyses of public policies and practices completed. Number of newly conducted gender analyses of public policies on the national and/or regional levels; 0; 0; 0; 11; 11; 5; Programme documentation. Number of public or local policies and practices realised which apply gender mainstreaming; 0; 0; 0; 13; 13; 5; Programme documentation. Output: Institutional capacity for gender mainstreaming established or strengthened. Number of organisations that have newly undergone gender audit; 0; 0; 0; 3; 3; 20; Programme documentation. Number of organisations with newly incorporated outcomes of gender audit into organisational and conceptual documents; 0; 0; 0; 3; 3; 10; Programme documentation. PA29 - Domestic and Gender-based violence. Outcome: Domestic violence reduced. Outcome indicator; 2013; 2014; 2015; Total. Number of clients/customers served by the institutions benefitting from the programme; 0; 0; 400; 400; 15; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of counseling/treatment programmes for offenders established; 0; 0; 0; 4; 4; 5; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Number of women's shelters or crisis centres supported; 0; 0; 0; 8; 8; 15; Programme Operator’s monitoring by the means of continuous and final reports of the Project Promoters. Output: Prevention of occurrence of domestic violence developed and improved. Number of conducted/published research or studies related to domestic violence; 0; 0; 0; 0; 0; 15; Programme documentation. Number of prepared educational or monitoring materials targeted at effecting change; 0; 0; 0; 12; 12; 20; Programme documentation. Output: Support and access for persons endangered and inflicted with domestic violence (including children, seniors and LGBT), and work with violent persons, improved. Number of services introduced/broadened for the protection of persons endangered and inflicted with domestic violence (including children, seniors, LGBT); 0; 0; 0; 13; 13; 20; Programme documentation. Number of violent persons included in the therapeutical and resocialisation programmes; 0; 0; 0; 132; 132; 20; Programme documentation. Outcome: Gender-based violence reduced. Outcome indicator; 2013; 2014; 2015; Total. Awareness on the harmful effects of GBV raised (survey); 0; 0; 0; 7; 7; 10; +10% Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Number of national strategies implemented to combat gender based violence; 0; 0; 0; 1; 1; 20; Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Number of policies, laws and regulations adopted or revised; 0; 0; 0; 0; 20; Monitoring by the Programme Operator by the means of continuous and final reports of the Project Promoters and the Programme Operator’s own survey (questionnaires) at the start and again at the end of the Programme implementation period.. Output: Prevention of occurrence of gender-based violence developed and improved. Number of educational modules for students created about gender-based violence; 0; 0; 0; 10; 10; 5; Programme documentation. Number of published/conducted research, campaigns, information events related to gender-based violence; 0; 0; 0; 31; 31; 30; Programme documentation. Output: Support for persons endangered and inflicted with gender-based violence improved. Number of (interdisciplinary) partnerships created/strengthened; 0; 0; 0; 71; 71; 30; Programme documentation. Number of support / prevention services introduced; 0; 0; 0; 32; 32; 20; Programme documentation....

CZ13: Domestic and Gender-based Violence & Mainstreaming Gender Equality and Promoting Work-Life Balance.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; n/a. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 1; 1; 0; n/a. PA28 - Mainstreaming gender equality and promoting work-life balance (Norway grant). Outcome: Balance between work, private and family life improved. Outcome indicator; 2013; 2014; 2015; Total. Number of comprehensive and integrated policies, particularly employment policies, aimed at promoting work/life balance implemented; 0; 0; 0; 0; 0; 5; Report provided annually by the Gender Equality Unit based on information provided by particular ministries.. Output: A methodological guide for practical and legal aspects of widening measures for improved balance between work and private life delivered. Methodological guide published and distributed by the end of the project; 0; 0; 0; 0; 0; 1; Methodological guide, distribution report, lists of participants, list of public authorities using the outputs of the methodological guide. Output: Media campaigns (website and conferences and other events) aimed at awareness raising in the field of balance between work, private and family life organized. Number of media campaigns launched (using TV spots, billboards, website, conferences, etc.).; 0; 0; 0; 0; 0; 1; Report with information on implemented media campaigns, records, lists of participants, articles in media, feedback documentation. PA29 - Domestic and Gender-based violence. Outcome: Domestic violence reduced. Outcome indicator; 2013; 2014; 2015; Total. Awareness on the harmful effects of domestic violence raised (survey); 0; 0; 0; 0; 0; 1; Input and output analysis of the domestic violence incidence and latency provided by an external subject. The analysis will also measure public awareness of domestic violence issues.. Number of measures in the scope of national strategies or actions plans to combat domestic violence developed and implemented; 0; 0; 0; 1; 1; 3; Report provided annually by the Gender Equality Unit. Each type of supported measure (i.e. analysis and studies, media campaign, conferences) will be counted as one indicator value.. Output: Analysis and studies on various issues connected to domestic violence delivered. Number of analysis and studies; 0; 0; 0; 0; 0; 7; Analysis and studies. Output: Media campaigns (website and conferences and other events) aimed at awareness raising in the field of domestic violence. Number of media campaigns launched (using TV spots, billboards, website, conferences, etc).; 0; 0; 0; 0; 0; 1; Report with information on implemented media campaigns, records, lists of participants, articles in media, feedback documentation....

CZ14: Schengen Cooperation and Combating Cross-border and Organised Crime, including Trafficking and Itinerant Criminal Groups.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2014; 2015; Total. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; Not Applicable. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; Not Applicable. Number of project partnership agreements in the beneficiary public sector; 0; 0; 0; 0; 2; Monitoring yearly and final reports of individual PDP and the entire PRG; Attendance sheets for particular events, minutes from meetings, reports from official trips, shared documents. PA30 - Schengen cooperation and combating cross-border and organised crime, including trafficking and itinerant criminal groups. Outcome: Development and improvement of structures, systems and technical equipment in order to improve the implementation of the Schengen acquis. Outcome indicator; 2014; 2015; Total. Number of airports with e-Gates installed and in operation.; 3; 0; 12; 12; 10; Reports from the Czech Police.. Number of travellers (individual border crossings) controlled by the electronic gates (per year).; 140,000; 0; 600000; 600000; 340,000; Monitoring reports, annual and final reports Electronic statistics maintained with the use of corresponding E-Gate functionality. (PDP 3). Output: Efficiency and security of the border control at international airports increased.. Delivery and installation of e-Gates for automated border checks at the international airport in Prague; 3; 0; 12; 12; 10; Monitoring reports, annual and final reports. Electronic statistics maintained with the use of corresponding E-Gate functionality. (PDP 3). The establishment of a functioning National Control Authority (NCA), including the purchase and installation of technology.; 0; 0; 0; 0; 1; Monitoring reports, annual and final reports (PDP 2). The number of full page document scanners purchased and installed at 5 international airports in the Czech Republic.; 0; 0; 80; 80; 80; Monitoring reports, annual and final reports. (PDP 3). The number of staff that effectively apply their skills learnt through training.; 0; 0; 18; 18; 45; Project reports. Output: Increased competence of law enforcement officers of the Schengen rules and the use of available technical equipment for cross-border police cooperation.. Number of law enforcement officers trained to prevent and combat cross-border and organised crime.; 0; 0; 0; 0; 250; Lists of participants from police staff training activities, invoicing documents, analyse of development of system EVIN, and its interaction with ETR etc. Regular monitoring reports, annual and final reports of particular PDPs Records in personal profiles of the participated staff (certificates of passing the courses, amendments in descriptions of professional duties of the staff including using the new IT systems, etc.) at the Personal Departments of the Police (PDP 1). Number of participants in work visits.; 0; 0; 7; 7; 50; List of reports from foreign trips, invoicing documents Regular monitoring reports, annual and final reports of particular PDPs Records in personal profiles of the participated staff (certificates of passing the courses, amendments in descriptions of professional duties of the staff including using the new IT systems, etc.) at the Personal Departments of the Police (PDP 1). Output: Planning and response time of the police improved.. An integrated secure automated search system for the databases accessible to the Czech Police developed.; 0; 0; 0; 0; 1; Continuous monitoring reports, annual and final reports PDP 5 Final report about PRG 5 Implementation studies, analyses and projects Delivery and transfer records, certificates of user training (PDP 5). Number of regional police headquarters equipped with the necessary technology for the use of geospatial information (GIS) by police officers in the field.; 0; 0; 0; 0; 8; Transfer records, user manuals, records of training of staff, etc (PDP 4). Outcome: Improved capacity to prevent and combat cross-border and organized crime, including trafficking in human beings and itinerant criminal groups. Outcome indicator; 2014; 2015; Total. An analysis of the effectiveness, the appropriateness and the impact of existing laws, strategies and action plans etc. relevant to policing minorities carried out.; 0; 0; 0; 0; 1; Project report. Output: Improved focus on Roma concerns in management strategies. Number of senior police management officials trained on how to improve the relationship between the police and the Roma communities; 0; 0; 10; 10; 10; Continous monitoring reports, annual and final reports (PDP 6). Output: The knowledge of how to improve the relationship between the police and the Roma communities strengthened.. Number of liaison minority police officers trained on how to improve the relationship between the police and the Roma communities; 0; 0; 15; 15; 15; Continuous monitoring reports, annual and final reports (PDP 6). Number of police specialists trained on how to improve the relationship between the police and the Roma communities.; 0; 0; 40; 40; 40; Continuous monitoring reports, annual and final reports (PDP 6)....

CZ15: Judicial Capacity-building Cooperation and Correctional Services, including Non-custodial Sanctions.. Programme indicators.. Indicator; Baseline; Achievement; Target; Source of Verification. Programme bilateral indicator; 2013; 2014; 2015; Total. Number of articles published in one country about the other partner country; 0; 5; 5; 3; Web pages of project stakeholders (i.e. Probation and Mediation Service, Prison Service of the CR, The Correctional Service of Norway, Ministry of Justice) and/or newspapers and magazines in the beneficiary and/or the donor country. Number of project partnership agreements in beneficiary civil society; 0; 0; 0; 0; 0; 0; N/a. Number of project partnership agreements in the beneficiary private sector; 0; 0; 0; 0; 0; 0; N/a. Number of project partnership agreements in the beneficiary public sector; 0; 0; 2; 0; 2; 2; Partnership agreement. PA31 - Judicial capacity-building and cooperation. Outcome: Improved efficiency of the court systems, including the development of systems for case handling. Outcome indicator; 2013; 2014; 2015; Total. Frequency of using videoconferencing in criminal procedings per year; 0; 0; 0; 0; 0; 250; Programme reports. Frequency of using videoconferencing in meetings, presentations and training per year; 0; 0; 0; 0; 0; 50; Programme reports. Output: Increase in the number of Justice staff able to use VC facilities.. Number of staff trained and able to use videoconferences.; 0; 0; 0; 0; 0; 369; Programme reports. Output: Increased use of videoconferencing facilities for the organisations in the justice sector.. Number of videoconferencing facilities; 5; 0; 0; 0; 0; 148; Programme reports. Outcome: Increased competence of actors within the judiciary. Outcome indicator; 2013; 2014; 2015; Total. Number of PMS employees who have succeeded in the final exam within the System of Further Education; 0; 0; 0; 0; 0; 50; Database of the PMS involving information about employees who passed the final exam. Output: PMS staff have increased competence in probation and mediatin skills.. Number of staff trained.; 0; 0; 0; 0; 0; 100; Programme reports. Output: Study materials / curriculum courses / syllabi / methodologies developed. Number of materials; 1; 0; 0; 24; 24; 38; Programme reports. Output: Supervision for lecturers provided.. Number of lecturers provided with supervision; 0; 0; 0; 32; 32; 30; Programme reports. PA32 - Correctional services, including non-custodial sanctions. Outcome: Improved competences of both inmates and prison staff. Outcome indicator; 2013; 2014; 2015; Total. Training curricula for initial and in-service training of prison staff reviewed/developed in accordance with European standards of the prison staff developed and used; 0; 0; 0; 0; 0; 1; Internal documentation and procedures of the Prison service (for example Regulation of the General Director). The category of document will depend on a decission of the management of the Prison Service.. Output: New programmes for treating prisoners or current programmes transferred to other prisons. Number of new programmes for treating prisoners or programmes transferred to other prisons; 0; 0; 0; 0; 0; 3; Programme reports. Output: The contents of courses developed.. Number of contents of courses developed.; 0; 0; 0; 0; 0; 7; Programme reports. Output: Training for prisons staff provided.. Number of prison staff better capable of dealing with juvenile prisoners, prisoners with drug addiction and other specific problems; 0; 0; 0; 0; 0; 617; Programme reports. Outcome: Increased focus on vulnerable groups in prison. Outcome indicator; 2013; 2014; 2015; Total. Number of persons participating in programme aimed at assisting vulnerable groups in prisons; 0; 0; 0; 0; 0; 50; Record about the number of participants of the programme, attendance lists from the consultations. Output: Legal consultancy for imprisoned foreigners available. Number of consultations provided for the imprisoned foreigners about admission and stay in the Czech Republic, social-legal matters, expulsion etc.; 0; 0; 0; 0; 0; 5; Programme report. Output: Materials for imprisoned foreigners available. Number of information and other material for imprisoned foreigners.; 0; 0; 0; 0; 0; 2; Programme report. Output: Prison staff better capable of treating foreign prisoners. Number of persons trained.; 0; 0; 0; 0; 0; 60; Programme report. Outcome: Overcome challenges connected to growing prison populations and prison overcrowding. Outcome indicator; 2013; 2014; 2015; Total. Number of prisons where the conditions of treating prisoners were improved; 0; 0; 0; 0; 0; 4; Documentation of the final approval of the renovation/construction. Output: Increased capacity of prison in line with international human rights standards. Number of prison cells in compliance with CoE standards; 0; 0; 0; 0; 0; 8; Programme report. Output: Increased capacity/space for training/education/work in the 4 prisons.. Number of places for training/education and work for prisoners; 0; 0; 0; 0; 0; 4; Programme report. Output: Newly built/expanded/reconstructed capacity for housing/production/shops/classrooms for prisoners and reconstructed space/grounds within prison area for sports or cultural activities for prisoners. Number of prisoners benefiting from the project; 0; 0; 0; 0; 0; 347; Programme report....